## Links
Technical Architecture | https://claude.ai/public/artifacts/27bcb80c-50a2-4662-ae51-44eed0a92fab
Yesly Charter | YESLY CHARTER
Landing Page | https://yeslifers.vercel.app/
Figma Designs | https://www.figma.com/proto/YLrKQ3S9MEzmPtaI8rodMo/House-of-Alpha?node-id=3758-4640&viewport=202%2C254%2C0.11&t=jXPvL6Sh4BCntJgw-1&scaling=scale-down&content-scaling=fixed&page-id=3692%3A2
Yesly Logo Images | Yesly Logo

## New User Flow
Screens | Screen name | Description | No of screens | Feedback
1 | Video 1 | Welcome & Set expectations | 1 |  | not skippable
2 |  | Login thru email id | 1 |  | Capturing - Emailid, Name
Popup - Welcome to Yeslifers
4 | Qts 1,2 & 3 | Where you are right now How does money feel Five years from now - what does good look like | 1 |  | in one single screen
7 | Sample Plan | In the app 2 pages (before after) Download pdf | 2 | Before & After (to be re-done by BBC Team for all the 6 avataars)
8 | Video 2 | Transition from sample plan to personal plan | 1 | Need Content from BBC | 30 sec video (non skippable)
9 | Compliance | Compliance | 1
10 | Feelings qts 1 | Money Journey - How has your money journey been? | 1 | Please reshare the content for this (here are the below optional options) Every inv done so far is beneficial Some hits, some misses Unlucky nothing has work
11 | Fact Qts 1 | Family details | 1 | We need some family tree concept over here which user can fill
12 | Fact Qts 2 | Assets In the bucket - Page 1 (Liquidable assets) In the bucket - Page 2 (Illiquid Assets) | 2
13 | Fact Qts 3 | Liabilities | 1
14 | Output 1 | Clarity Insight - NW + War | 3
15 | Output 1 | Clarity Insight - Projections | 3
16 | Output 1 | Clarity Insight - Blindspots | 3
17 | Video 3 | Transition from free to paid user (explanation of paywall & connecting the sample plan with the data they provided and what all data to provide) | 1 | Need Content from BBC | 30 sec video (non skippable)
18 | Fact Qts 4 | Life events / Goals | 2
19 | Fact Qts 5 | Income | 1
20 | Fact Qts 6 | Expenses (Compulsory, Discretionary, Inv) | 1
21 | Fact Qts 7 | Insurances (Life & Health)
22 | Output 2 | Assets, Liabilties, Income, Expenses, Surplus & timeline life events chart | 1
23 | Payment Page | Paywall | 1
24 | CTA | If option 1 selected & payment made then download the FP & Action Plan
25 | CTA | If option 2 selected & payment made
26 | Video 4 | Harish's Video on IP (common video) | 1 | Need Content from BBC | 30 sec video (non skippable)
27 | AA | Collect info thru AA (Assets, Liabilties, Bank Statements)
28 | CTA | Download FP+IP (Summary in the app)
29 | CTA | Action Plan

## Third Party Integrations
Thirdaprty Integrations | Requirement in app
AA (like finvu) | If the user chooses to pay for Paywall 2 & 3, then we will first collect details from AA and the show the Inv Plan
Bse Star | After execution plan is presented and user wants to execute from our platform
Small gateway | After execution plan is presented and user wants to execute from our platform
Sms provider (like twilio)
Mail provider (like sendgrid)
Martech platform (like mixpanel)
Blogs (like ghost)
KYC (via KRA, CVL/CAMS/DIGILOCKER) | Need to check with legal team, where should we do the KYC
push notification (firebase/apms/gcm)
HoA planning APIs | For all the outputs - after collecting all the data
Zerodha?
Data source (like cmots/accord/value reasearch)
There may be 2-3 smaller integrations like bank ifsc master etc

## Workstream
Workstream | Objective | Priority | Deadline | Primary Owner | Secondary Owner | Status
Technical Architecture | Finalize architecture, and execution roadmap | High | 2026-05-24 | Vatsal | Gaurav | Complete
Developer Finalisation | Finalize technology partner, architecture, and execution roadmap | High | 2026-06-08 | Vatsal |  | In-Discussion
Content for marketing & landing page | Community Landing Page Content and Marketing Content for community awarness | High | 2026-06-11 | Somil | Bhuvanaa
Content for app | Close out on the flow, content and precise requirement from app | High | 2026-06-08 | Somil | Bhuvanaa
Finalising Designs with Ihstiaq & BBC | Finalize UI/UX design direction, branding alignment, and design system | High | 2026-06-12 | Somil | Bhuvanaa
Prepare the Sample Plan | Create sample user/advisory plans for platform structure and presentation | High | 2026-05-26 | Somil | Bhuvanaa | To be discussed with Core
Community Flow & App Flow | Define complete user journey and engagement structure | High | 2026-06-08 | Somil | Kajal
Community App & Integration Ecosystem | Build the community platform and integrations | High | 2026-06-14 | Vatsal | Kajal
MVP for Financial Planning | Launch the first version of the financial planning module | High | 2026-06-14 | Somil | Bhuvana
Advisory Framework | Create the advisory servicing and consultation model | Mid to High | 2026-06-21 | Somil | Harish
Operations & Governance | Establish operational structure, ownership, and reporting | Mid to High | Ongoing | Somil | Kajal
Implementation of Advisory | Build execution workflows for investments and recommendations | Low | TBD | Kajal | Somil
Growth & Engagement Strategy | Drive community acquisition, engagement, and retention | Low | TBD | Bhuvana | Vatsal
Third Part Integrations - AA Integration / BSE / Smallcase

## Community
Sr No | Workstream | Objective | Key Activities | Deliverables | Timeline
1 | Community Strategy & Positioning | Define purpose, audience, and value proposition | Define vision, mission, target member persona, community purpose, community rules and code of conduct | Community Charter, Member Guidelines, Value Proposition | Week 1
2 | Branding & Identity | Create a strong and professional community brand | Finalize community name, tagline, logo, WhatsApp banner, LinkedIn banner, visual identity | Community Brand Kit | Week 1
3 | LinkedIn Marketing Strategy | Build awareness and attract founding members | Define content pillars, content themes, posting schedule, launch campaign, founder story, engagement strategy | 30-Day LinkedIn Content Calendar | Week 1
4 | Community Infrastructure | Set up all platforms and operational structure | Create WhatsApp Community, Discussion Group, Announcement Group, Admin Structure, Welcome Messages | Community Setup Complete | Week 1
5 | Community Growth | Acquire initial founding members | Personal outreach, LinkedIn engagement, referrals, invite campaigns, registration management | First 100 Founding Members | Weeks 2–6